## Read me first
Risk management
1. Why use a risk management template?
Identifying, assessing, managing and following risks are an essential part in the project’s preparation and implementation processes. It helps us to prepare for situations that would otherwise impact negatively the project. While reflecting over the risks of the project we are able to identify vulnerable areas and find appropriate measures to deal with the risks.
2. When should you fill in the template?
The template should be used both during the project design phase as well as during the implementation of the project. Every project has risk areas and creating a risk management plan when designing the project demonstrates understanding of the project implementation processes. Once the project starts it is important to continue to identify risks and develop management plans. Equally important is to follow-up the risks and see if, after managing them, the solutions developed and applied where successful or if you need to manage further the risks.
3. Who should fill in the template?
All project partners should be involved in the process of identifying and assessing the risks as each partner has a different capacity and experience in international projects as well as different resources that can be made available and put at the disposal of the project. This means that the risks can be different from a project partner to another. The management of the risks will be done by those appointed. The following of the risks can be done by the project manager together with those appointed to apply the risk management plan. All the other project partners should be regularly informed about how the managing of the risks proceeds. All project partners should be involved in the process of identifying and assessing the risks as each partner has a different capacity and experience in international projects as well as different resources that can be made available and put at the disposal of the project. This means that the risks can be different from a project partner to another. The management of the risks will be done by those appointed. The following of the risks can be done by the project manager together with those appointed to apply the risk management plan. All the other project partners should be regularly informed about how the managing of the risks proceeds.
4. How to use this template?
The template is composed of the next: - Read me first - Risk management - Examples of risk management - Drop down list The risk management template includes four main sections: IDENTIFICATION, ASSESSMENT, MANAGEMENT and FOLLOW-UP. The users should fill in all the questions corresponding to all four categories. Column A, D, E and I have drop down lists from where different alternatives can be chose. If the users of the timesheet feel necessary to change the risk areas they can do so in the page called "drop down list". Once the relevant names in the drop down list will be changed the field concerned will be automatically changed in the document and will be visible when selected in each page. Columns D and E present the probability that a risk will become a reality and respectively the impact that the risk would have over the project if that will become a reality. Columns D and E will change color depending on the value chosen. For the purpose of simplification a high probability for the risk to happen combined with a high impact of the risk will be called severity of the risk. If needed, the user can use the “Sort & Filter” function and sort the risks based on the severity of the risks. The severity of the risks is given by the color of the cells. It is important that the user is also following the status of the risk after implementing the management plan described in cell F. If it is considered that there is still severe a second management should be drafter and implemented until the risks reaches a level of risk safety. The document has several formulas and it is protected so that the users will not delete or change any formulas by mistake. Those wishing to change the formulas in the document can do so by introducing the password when requested. The password is pie+.
5. About the risk management template
The risk management template was developed as part of the strategic partnership "Project Instruments for Erasmus+ (PIE+) financed by the Swedish National Agency and implemented between November 2015 - June 2017. More information about the partners, the project and its objectives as well as other instruments developed in the project can be found at: www.erasmustools.eu The PIE+ logo will not be visible when the risk management template will be printed.

## Risk management
IDENTIFICATION |  | ASSESSMENT |  |  | MANAGEMENT |  |  | FOLLOW-UP
Risk area | Describe the risk and What could go wrong | Expected impact on the project, budget and/or result | Which are the chances for the risk to take place? | How strongly it would affect the project? | What will you do to avoid the risk? | Who manages the risk? | Deadline | Status

## Examples of risk management
IDENTIFICATION |  | ASSESSMENT |  |  | MANAGEMENT |  |  | FOLLOW-UP
Risk area | Describe the risk and What could go wrong | Expected impact on the project, budget and/or result | Which are the chances for the risk to take place? | How strongly it would affect the project? | What will you do to avoid the risk? | Who manages the risk? | Deadline | Status
Activities | Short period of time in which to select the participants can influence the no of participants that can participate in the TC in October. The reimbursement coming after the end of the project can influence the no of participants participating in the TC in October | Not enough participants for the TC in Greece or an unequal number of participants from different countries | Medium | Low | 1. SALTO announcement (with mentioning that the reimb is done later); 2. Share the call among own international networks; 3. Email the NA about the permission to readjust the no of participants based on the changes in the no of participants per country | PMG | 25.09.2016 | On-going

## Drop down lists
Risk description | Risk level | Status
Project management | Low | On-going
Intellectual outputs | Medium | Done
Objectives | High
Activities
Budget, Target group
External factors
Other